Request for Change

RFC-001

1. Change Identification

| RFC Number: | RFC-001 |
| --- | --- |
| Date Submitted: | 2026-02-15 |
| Requested By: | Benjamin Lamb, BET Division |
| Change Title: | Upgrade R1 and R2 IOS from 16.10.3a to 16.12.x |
| Priority: | Medium |
| Target Date: | 2026-02-22 |
| Maint. Window: | Saturday 0800–1200 (lab not in use) |

2. Description of Change

What is being changed and why?

Upgrade the IOS XE software on both core routers (R1 and R2, ISR 4221) from version 16.10.3a (ISR4200-ucmk9.16.10.3a.SPA.bin) to version 16.12.x (isr4200-universalk9_ias.16.12.05.SPA.bin). The upgrade addresses known bugs in the 16.10 train and provides improved SSH and OSPF stability. The universalk9_ias image also includes the IP Base and Security feature sets needed for our lab configuration.

3. Affected Devices & Services

| Hostname | Model | Change Summary | Risk Level |
| --- | --- | --- | --- |
| R1 | ISR 4221 | IOS XE upgrade 16.10.3a → 16.12.x | Medium |
| R2 | ISR 4221 | IOS XE upgrade 16.10.3a → 16.12.x | Medium |
| SW-DIST | Catalyst 1000 | No change (verify trunks post-upgrade) | Low |
| SW-ACC | Catalyst 2960 | No change (verify connectivity) | Low |

4. Implementation Plan

Step-by-step procedure:

1. Back up running-config on R1 and R2 (see docs/runbooks/backup-restore.md) 2. Verify current IOS version: show version 3. Prepare USB drive with new IOS image 4. Upgrade R1 first (see docs/runbooks/ios-upgrade.md): a. Console into R1, insert USB, enter ROMMON b. Boot from USB, delete old IOS, copy new to bootflash c. Set boot variable, verify, reload 5. Verify R1: show version, show standby brief, show ip ospf neighbor 6. Once R1 is stable, repeat steps 4–5 for R2 7. Verify full network convergence (see verification section)

5. Rollback Plan

If the change fails, how do we revert?

1. If new IOS fails to boot: enter ROMMON and boot from USB drive (old image or new) 2. If configs are lost: restore from golden configs (configs/golden/R1.txt, R2.txt) 3. Restore order: R1 first, then R2 (R1 is NTP master and default-route originator) 4. Estimated rollback time: 15 minutes per router 5. If both routers fail simultaneously: SW-DIST and SW-ACC remain operational for local VLAN traffic; inter-VLAN routing and internet access will be down until at least one core router is restored.

6. Testing & Verification

How do we confirm the change was successful?

On R1 and R2 after upgrade: • show version — confirm new IOS version string • show ip interface brief — all interfaces Up/Up • show standby brief — HSRP states correct (R1 Active VL10/40, R2 Active VL20) • show ip ospf neighbor — full adjacency with expected neighbors • show ip ssh — SSH version 2 enabled • show ntp status — R1 master, R2 synced End-to-end tests: • PC-A (VLAN 10): ping 192.168.10.1, ping 192.168.30.10, ping 8.8.8.8 • PC-C (VLAN 20): ping 192.168.20.1, ping 192.168.10.1 (inter-VLAN) • SRV-1 (VLAN 30): ping 192.168.10.1 (confirms WAN + OSPF)

7. Approval

| Role | Name | Date | Approved? |
| --- | --- | --- | --- |
| Submitted By | Benjamin Lamb | 2026-02-15 | Yes |
| Instructor / Lab Admin | Benjamin Lamb | 2026-02-15 | Yes |
| IT Department | N/A (lab network) | — | — |

8. Post-Implementation Review

| Change Completed: | Yes |
| --- | --- |
| Completion Date: | 2026-02-22 |
| Issues Encountered: | None. Both routers upgraded successfully in sequence. Total downtime: ~40 minutes. |
| Docs Updated: | CHANGELOG.md, KNOWN_ISSUES.md (IOS upgrade history), inventory/ITN101_Network_Inventory.xlsx (firmware column) |

End of RFC